## Work Requests Edit1
Subject | Short Description | Campus | Organization Type | Type | Business Unit | Primary Contact | Level of Effort | Priority | Ranking | Date Submitted | Coordinator | Developer | Last Updated | HRIS Status | Change Control # | Notes | System Impacted | Mandatory? | Last Updated Date | Production Date
WR-7020 Fidelity Log File Clean-up | Following 3 issues need to be addressed. 1. There are two places in the log file where SSN is being written out where we would like the SSN reference removed 2. There is a missing space in one of the queries generating an oracle error in the log file. Stephanie has the specific query. 3. Exception in the log file that seems to be related to emailing done within the application. Stephanie has specific example. | UA;UIC;UIS;UIUC | ADSD | WR - ADSD HR Payroll |  | Cummings, Stephanie | Low | Low |  | 2016-08-06 | Cummings, Stephanie |  |  |  |  | 1/12 Developer was requested on 12/20. | Fidelity | Yes | 2017-01-12
WR-6815 Summary Report for CMS Employer Component | Create A Summary Report for CMS Employer Component Work with UAFR to create a summary report related to the employer component of health, life, dental insurance for CMS. Initial thinking is that the report would contain UIN, $ totals and other data elements used in the calculation of the premium cost, and totals would agree to the CMS data file. UAFR would then use this summary report from the CMS process to independently verify the accuracy and completeness of the calculation on a regular basis. |  | ADSD | WR - ADSD HR Payroll |  | Rasmus, Brent | High | Medium | 44 | 2014-12-08 | Cummings, Stephanie |  |  |  |  | 1/12 Meetings are scheduled for January 2017 to determine how this report should be rebuilt given the CMS outsourcing to Morneau Shepell. | CMS Contribution | No | 2017-01-12
WR-6814 Decommission Internal T_GXRDIRD_History Table | Decommission Internal T_GXRDIRD_History Table |  | ADSD | WR - ADSD HR Payroll |  | Presson, Sherri Carlene | Low | Low | 37 | 2014-07-18 | Robinson, Kathi |  |  |  |  | 1/12/17 On Hold per UPB. As of 2/2/16, Larry is reviewing the spreadsheet showing who has access to the old customer history table and who has access to the new Banner history table. Next step will start after we get his input on this. |  | No | 2017-01-12
WR-5780 Work Request needed for Nessie ADD Application A copy of ... | Work Request needed for Nessie ADD Application A copy of the Nessie ADD application at https://nessieptest.uihr.uillinois.edu/cf/ADD/login.cfm was tested on May27, 2014 using Appscan. 2 High severity and 11 Medium severity issues were found. Details in reports starting with "20140527_Nessie_ADD..." are located at \\ui\aits\AppScan Reports & Scans\Nessie_ADD\Reports<file:///\\ui\aits\AppScan%20Reports%20&%20Scans\Nessie_ADD\Reports> Please email me if you have any questions Thanks, Dan Lapp (dlapp@uillinois.edu<mailto:dlapp@uillinois.edu>) |  | ADSD | WR - HR Applications |  | Lapp, Daniel | Low | Low |  | 2014-05-27 | [7 empty] | No | 2016-06-10
UPB-1133 Modify HRPAY_AUDIT_PRE_DOCM_CHN | Modify the HRPAY_AUDIT_PRE_DOCM_CHN in the Adjustment Calc |  | ADSD | WR - ADSD HR Payroll |  | Andrea Lasticly | Low | Low |  | 2017-01-18 | Robinson, Kathi |  |  |  |  | 1/18 Assigned to Kathi. |  | No | 2017-01-18
UPB-1132 Update BANNER with U.S. Tax Update #: 231 | BANNER new tax updates for CO, IN & ND | UA;UIC;UIS;UIUC | ADSD | WR - ADSD HR Payroll |  | Andrea Lasticly | Low | Low |  | 2017-01-13 | Velazquez, Robyn |  |  |  | 15920 | 1/18 Scheduled for production on Jan 19, 2017. | Banner Human Resources | Yes | 2017-01-18 | 2017-01-19
UPB-1127 Add Pre-docm audits to BW and MN chains | Add the pre-docm audits to BW and MN payroll calcs |  | ADSD | WR - ADSD HR Payroll |  | Andrea Lasticly | Low | Low |  | 2016-10-18 | Robinson, Kathi |  |  |  |  | 1/12 UPB is reviewing the scripts. Will review with UPB on Jan 24th, if we don't get sign-off prior. |  | No | 2017-01-12
UPB-1125 Record Fail when updating in Tax Navigator | Incorrect subcode causes record to fail when updating in Tax Navigator |  | ADSD | WR - ADSD HR Payroll |  | Andrea Lasticly | Low | Low |  | 2016-09-16 | Kittell, David |  |  |  |  | 1/12 Reviewed Banner configuration with Ellucian. They indicated that our config was not correct. Larry will modify setup and test in 2017. |  | No | 2017-01-12
UPB-1123 SURS Contribution File to Accept Plan Code 05 | Modify the SURS Contribution file to accept Plan Code 05 to accommodate a new plan code for RS After discussions on Sept 29th, 2016 - UPB recommends looking at other options to handle this one person. |  | ADSD | WR - ADSD HR Payroll |  | Andrea Lasticly | Low | Low |  | 2016-08-31 | Cummings, Stephanie |  |  |  |  | 10/3 On Hold. UPB would like to pursue other options rather than modifying the SURS Contribution File to handle this. Currently, one 1 person in this situation. |  | No | 2016-10-03
UPB-1118 Parking Deductions for Academic Professional Employees | Parking Deductions for Academic Professional Employees |  | ADSD | WR - ADSD HR Payroll |  | Andrea Lasticly | Low | Low |  | 2016-08-22 | Cummings, Stephanie |  |  |  |  | 1/12 UPB has given this priority. Analysis is needed. |  | No | 2017-01-12
UPB-1107-LTD Deduction Adjustment Email | Correction to the logic used to generate the UI New Hire LTD Deduction Adjustment email. When an employee clicks the “Submit” button on the LTD enrollment form in UI New Hire, an email is automatically generated regarding the potential need for a deduction adjustment based upon current logic. If the parameters of the logic are met, then this email is generated regardless of whether the employee selects "Yes" that they would like to enroll in LTD or "No" they would not like to enroll in LTD. This work request is to only generate the email if the parameters of the logic are met *and* the employee selects “Yes” that they would like to enroll in LTD. | UA;UIC;UIS;UIUC | HRIS - ADSD | WR - ADSD HR Payroll | UPB | Becker, Zac | Low | Low |  | 2016-04-25 | Royce-Malmgren, Katrina |  | 2016-07-19 | Specs in Progress |  |  | UI New Hire | No | 2016-09-09
UPB-1106 Assess impact of new State Tax Code format | Assess impact of using new format of State Tax Code format beyond SS% Proposed using ST% | UA;UIC;UIS;UIUC | ADSD | WR - ADSD HR Payroll |  | Andrea Lasticly | Low | Low |  | 2016-03-21 | Presson, Sherri |  |  |  |  | 1/12 Ready to test Involuntary Calc Engine. Analysis has shown that the involuntary calc engine will need updated to accommodate the new naming convention. UPB gave the approval to start work on this. Intellichek and Online Earnings look to be okay. UPB will need to update their databases. |  | No | 2017-01-12
UPB-1100 PARIS Issue ID 8681 | Deductions that are marked Active or Exempt for a Pay Event but are terminated on the last day of the pay event are showing as terminated when pulled into an adjustment for that pay event |  | ADSD | WR - ADSD HR Payroll |  | Larry Hanyzewski | Low | High |  | 2016-03-09 | Robinson, Kathi |  |  |  |  | 8/8 Not started | Payroll Adjustment Request Interface System (PARIS) | No | 2016-08-08
UPB-1098 PARIS Issue ID 8667 | Transaction history should not be visible if user doesn't have security access to an employee This year. |  | ADSD | WR - ADSD HR Payroll |  | Larry Hanyzewski | Low | High |  | 2016-03-09 | Robinson, Kathi |  |  |  |  | 8/8 Not started. | Payroll Adjustment Request Interface System (PARIS) | No | 2016-08-08
UPB-1097 PARIS Issue ID 8658 | Adjustment for Separation payout allowed an earn code the job was not eligible for. This year. |  | ADSD | WR - ADSD HR Payroll |  | Larry Hanyzewski | Low | High |  | 2016-03-09 | Robinson, Kathi |  |  |  |  | 8/8 Not started - needs to be addressed during the 2016 calendar year. | Payroll Adjustment Request Interface System (PARIS) | No | 2016-08-08
UPB-1096 PARIS Issue ID 8656 | "Comments added to Banner should have the same timestamp from the memo tab. This year." |  | ADSD | WR - ADSD HR Payroll |  | Larry Hanyzewski | Low | High |  | 2016-03-09 | Robinson, Kathi |  |  |  |  | 8/8 Not started. Needs to be completed in calendar year 2016. | Payroll Adjustment Request Interface System (PARIS) | No | 2016-08-08
UPB-1095 PARIS Issue ID 8645 | Add ability to add attachments to PARIS transactions. |  | ADSD | WR - ADSD HR Payroll |  | Larry Hanyzewski | Low | High |  | 2016-03-09 | Robinson, Kathi |  |  |  |  | 8/8 Not started. Needs to be completed in calendar year 2016. | Payroll Adjustment Request Interface System (PARIS) | No | 2016-08-08
UPB-1094 PARIS Issue ID 8637 | Exception Time Employee should be required to use timesheet if it's still open. | UA;UIC;UIS;UIUC | ADSD | WR - ADSD HR Payroll |  | Larry Hanyzewski | Low | Medium |  | 2016-03-09 | Robinson, Kathi |  |  |  |  | 8/8 Not started. Depending upon the FLSA decision - this could become a high priority. | Payroll Adjustment Request Interface System (PARIS) | No | 2016-08-08
UPB-1093 PARIS ISSUE ID 8615 | Refresh PUA deduction list if deductions have been added or removed from Banner. |  | ADSD | WR - ADSD HR Payroll |  | Larry Hanyzewski | Low | High |  | 2016-03-09 | Robinson, Kathi |  |  |  |  | 8/8 Not started. Needs to be completed in calendar year 2016. | Payroll Adjustment Request Interface System (PARIS) | No | 2016-08-08
UPB-1090 PARIS PUA STAT REPORTS | PB in need of 2 reports in regards to PARIS PUAs. Sum and detail reports (Dept PUA Data) DK has specs from Larry and Laura Report of # PUA Returned to Dept Breakdown of Reason Why Returned See Larry for Detail All reports needed 1/4'ly by calendar year |  | ADSD | WR - ADSD HR Payroll |  | Larry Hanyzewski | Low | Low |  | 2016-03-03 | Robinson, Kathi |  |  |  |  | 8/8 Will be starting week of 6/13/2016. Per Larry, this should be done right after the PEDA reports. |  | No | 2016-08-08
UPB-1087 Modify PDABENE & PDABCOV Access | Modify PDABENE & PDABCOV Access |  | ADSD | WR - ADSD HR Payroll |  | Andrea Lasticly | Low | High |  | 2016-02-04 | Woodley, Teresa |  |  |  |  | 10/3/2016- Waiting for next steps | Banner Human Resources | No | 2016-10-03
UPB-1084 HRFE:Remove FYI's | 8560 - CR: CR1265: UPB: Remove FYI's from Grads, Hourlies and Students routed for ADD, ERC and REA. |  | ADSD | WR - ADSD HR Payroll |  | Brenda Butts | Low | Medium |  | 2016-03-04 | Robinson, Kathi |  |  |  |  | 8/8 Not Started. | HR_Front_End (HRFE) | No | 2016-08-08
UPB-1081 New mass time feeder file for Beckman Institute UIUC | New mass time feeder file for Beckman Institute | UIUC | ADSD | WR - ADSD HR Payroll |  | Andrea Lasticly | Low | Low | 56 | 2015-11-13 | Combs, Mary |  |  |  |  | 8/8 On Hold per UPB. |  | No | 2016-08-08
UPB-1080 New mass ttime feeder for Business Service Center at UIUC | New mass ttime feeder for Business Service Center at UIUC | UIUC | ADSD | WR - ADSD HR Payroll |  | Andrea Lasticly | Low | Low | 55 | 2015-11-13 | Combs, Mary |  |  |  |  | 8/8 On Hold per UPB. |  | No | 2016-08-08
UPB-1079 HRFE/ANA Terminated Org Identification - Quarterly | We are needing a HRFE/PARIS security review for invalid ORGs. We would like Dave Kittell to write the sql to identify the UINs that have the invalid ORGs that will need to be cleaned up. |  | ADSD | WR - ADSD HR Payroll |  | Gorrell, Cheri L | Low | Low | 54 | 2012-08-28 | Kittell, David |  |  |  |  | 8/8 On Hold per UPB. Because of need to view historical transactions, org access cannot be removed. No HRFE access was found for removal. Dave will remove PARIS access created at go-live that is not needed and leave the rest. |  | No | 2016-08-08
UPB-1078 Adjustments not on SDU File/Transmittal Summary | Adjustments not on SDU File/Transmittal Summary |  | ADSD | WR - ADSD HR Payroll |  | Andrea Lasticly | Low | Low | 48 | 2015-10-22 | Combs, Mary |  |  |  |  | 8/8 On Hold per UPB. | Involuntary Deduction | No | 2016-08-08
UPB-1077 Calc Engine IFT deduction | Calc Engine IFT deduction - MN10 calcan over-deduction for IFT was processed | UA;UIC;UIS;UIUC | ADSD | WR - ADSD HR Payroll |  | Andrea Lasticly | Low | Low | 53 | 2015-10-22 | Combs, Mary |  |  |  |  | 8/8 On Hold per UPB. Analysis is in progress - low priority. |  | No | 2016-08-08
UPB-1069-Correct SRA Application Contributions | UI New Hire and NESSIE: Refactor app, including: 1. Change how the user’s current deductions are retrieved from Banner. 2. Change the user interface elements to be more intuitive for entering contributions. 3. Add a fancy JavaScript calculator to calculate the user’s contributions instead of submitting the whole form back to the server for calculations. 4. Improve usability, streamline code, remove redundant code, etc. 5. Change process for switching from % to flat rate and vice versa (currently two separate forms must be submitted). 6. Possibly put in some thresholds of some kind: so that 403(b) contributions greater than a certain % of employee salary cannot be submitted (or a warning is provided) - basically something to prevent the scenario where the employee's whole paycheck will not be wiped out by their 403(b) contributions. | UA;UIC;UIS;UIUC | HRIS | WR - ADSD HR Payroll | UPB | Devaney, Carole | Low | Low |  | 2014-03-06 | Zepeda, Ernesto |  | 2016-07-19 | Specs in Progress |  |  | NESSIE | No | 2016-11-14
UPB-1054 CMS Contrib File MisHandling of Domestic Partner/Civil Union | CMS Contrib File MisHandling of Domestic Partner/Civil Union |  | ADSD | WR - ADSD HR Payroll |  | Cummings, Stephanie M | Low | Low | 16 | 2015-08-29 | Robinson, Kathi |  |  |  |  | 8/8 On Hold per UPB. CU and DP rates were loaded into the CMS Contribution reimbursement rates table on 1/21/16. This will make the logic easier since the rates will be able to be looked up. Working on logic changes now. | CMS Contribution | No | 2016-08-08
UPB-1044 Modify DEDN-NTOT Query | University Payroll and Benefits requested that AITS TAMS HR modify the query DEDN-DTOT to use a configuration table. |  | ADSD | WR - ADSD HR Payroll |  | Lasticly, Andrea M | Low | Low | 50 | 2015-06-23 | Stone, David |  |  |  |  | 8/8 On Hold per UPB. UPB will need to provide rules for determining 1042 deductions. |  | No | 2016-08-08
UPB-1043 Mass Time Edit Modifications for RP/TW/TB | Mass Time Edit Modifications for RP/TW/TB |  | ADSD | WR - ADSD HR Payroll |  | Hanyzewski, Larry | Low | Low | 17 | 2015-06-17 | Stone, David |  |  |  |  | 8/8 On Hold per UPB. |  | No | 2016-08-08
UPB-1040 New Mass Time Entry Feeder Request for Biologic Resources Laboratory (UIC) | New Mass Time Entry Feeder Request for Biologic Resources Laboratory (UIC) |  | ADSD | WR - ADSD HR Payroll |  | Hanyzewski, Lawrence V. | Low | Medium | 35 | 2015-05-29 | Combs, Mary |  |  |  |  | 8/8 On Hold per UPB. On Hold. Other feeder projects are in line ahead of this one. |  | No | 2016-08-08
UPB-1037 Appworx Modifications to Loading Retro Pay Files | UPB Ops and Production requests that AITS move the Retro Pay chain to BW Day 1 and the MN Day 0 and write a script to identify duplicate earn codes on special rates earnings by person. This audit will be placed in the payroll audit queries that Kathi Robinson is working on/with. |  | ADSD | WR - ADSD HR Payroll |  | Lasticly, Andrea M | Low | Low | 11 | 2015-05-19 | Kittell, David |  |  |  |  | 8/8 On Hold per UPB. Modifications have been made and tested. Need to discuss with UPB the need for additional testing and production time frame. |  | No | 2016-08-08
UPB-1036 Payroll Mass Time Feeder: UIC Parking | Work Requests for the UIC Parking - Payroll Mass Time Entry Feeder Project UPB Ops and Production is submitting a work requests to AITS for the UIC Parking, Payroll Mass Time Entry Feeder Project. |  | ADSD | WR - ADSD HR Payroll |  | Lasticly, Andrea M | Low | Medium | 61 | 2015-04-28 | Combs, Mary |  |  |  |  | 8/8 On Hold per UPB. Waiting on client to develop their processes. |  | No | 2016-08-08
UPB-1033 Modify TDRP Update | Modify TDRP Update Modify HRPAY_M_Benefits_Deduction_Update informatica job. Right now, it is only updating Amount2 from the input file if the deduction code is between 'T01' and 'T12'. This means the program is not updating Amount2 for the Terminal Benefits and Roth 403B deduction codes. I would like this edit changed to update Amount2 for any deduction codes where ptrbdca_bdty_code = '10' and ptrbdca_amount2_ind <> 'N'. See attached email for where in the informatica job needs updated. |  | ADSD | WR - ADSD HR Payroll |  | Becker, Zac | Low | Medium | 24 | 2015-03-31 | Cummings, Stephanie | Thompson, Mark |  |  |  | 8/8 On Hold per UPB. For 2016 it has been decided that we will update via scripts like last year. Going forward - this is a place holder so we do not forget this issue needs addressed before Spring 2017. If the Automated Deduction Loader gets completed - this process will no longer be needed as we can use the deduction loader. |  | No | 2016-08-08
UPB-1032 Expansion of the E- IWO | Expansion of the E- IWO |  | ADSD | WR - ADSD HR Payroll |  | Lasticly, Andrea M | Low | Low | 28 | 2015-03-25 | Combs, Mary |  |  |  |  | 8/8 On Hold per UPB. Not started. We will expand to accept electronic from all states. There is no deadline. More filler work. | Involuntary Deduction | No | 2016-08-08
UPB-1031 TIAA Cref Program Modifications | TIAA Cref Program Modifications |  | ADSD | WR - ADSD HR Payroll |  | Hanyzewski, Larry | Low | Medium | 45 | 2015-03-07 | Cummings, Stephanie |  |  |  |  | 8/8 On Hold per UPB. This is really just a place holder. Stephanie did some initial analysis. | TIAA/CREF Interfaces | No | 2016-08-08
UPB-1030 BDMS Transfer Process Modifications | BDMS Transfer Process |  | ADSD | WR - ADSD HR Payroll |  | Lasticly, Andrea M | Low | High | 2 | 2015-02-26 | Combs, Mary |  |  |  |  | 1/12 BSS will be looking into updating the BSCAC application so that the image files and scan index files are saved directly to the appropriate location on docmgtprod. |  | No | 2017-01-12
UPB-1029 SURS Contrib Error Modifications | SURS Contrib Error Modifications I need the following two changes made to the SURS Contribution file: Change #1: Add A1 and A2 to Case 2: Employee has limit plan but has not reached his limit. Right now it's falling into Case4: Invalid Plan Code, which is incorrect. Change #2: Split out cases 0, 1, and 4 into new Error 009 - Invalid Plan Code. Convert Cases 2 & 3 to a warning rather than an error. Supplemental Info value changes for cases 2 & 4 to include A1 and A2. |  | ADSD | WR - ADSD HR Payroll |  | Hanyzewski, Larry | Low | Medium | 23 | 2015-02-18 | Cummings, Stephanie |  |  |  |  | 8/8 On Hold per UPB. Testing/development iteration was in progress. | SURS Contributions | No | 2016-08-08
UPB-1026 Review Banner PXR1042 Report | Review Banner PXR1042 Report |  | ADSD | WR - ADSD HR Payroll |  | Hanyzewski, Larry | Low | Low | 27 | 2015-01-16 | Presson, Sherri |  |  |  |  | 8/8 On Hold per UPB. PXR1042 was run in BANDEV on 1/22/15 and placed on the Payroll/AITS shares for UPB to review. UPB has not had time review. | Banner Human Resources | No | 2016-08-08
UPB-1025 Modify Validation 20 Batch Application to Consolidate Dupe FOAPs | Validation 20 Report and duplicate FOA Please modify the Validation 20 to consolidate duplicate FOAPALs. Contact Ops and Production for more information. |  | ADSD | WR - ADSD HR Payroll |  | Lasticly, Andrea M | Low | Low | 39 | 2014-12-16 | Cummings, Stephanie |  |  |  |  | 8/8 On Hold per UPB. | FOAPAL Validation Status | No | 2016-08-08
UPB-1023 Automated Deduction Loader | Automated Deduction Loader In general the process would ideally eliminate our need to use the Banner delivered mass update deduction process when loading population selections, and other less desirable batch processes currently used to create employee deduction records in mass. |  | ADSD | WR - ADSD HR Payroll |  | Gavin, Tim | Low | Medium | 25 | 2014-11-20 | Chalfant, Russell |  |  |  |  | 8/8 On Hold per UPB. |  | No | 2016-08-08
UPB-1020 Investigate Adjustment Form Showing Calculated Amount | Investigate Adjustment Form Showing Calculated Amount |  | ADSD | WR - ADSD HR Payroll |  | Hanyzewski, Larry | Low | Low | 38 | 2014-10-10 | Chalfant, Russell |  |  |  |  | 8/8 On Hold per UPB. | Banner Human Resources | No | 2016-08-08
UPB-1019 Investigate Use of Prompt #5 on PZPDIRD | Investigate Use of Prompt #5 on PZPDIRD |  | ADSD | WR - ADSD HR Payroll |  | Hanyzewski, Larry | Low | Low | 32 | 2014-10-10 | Chalfant, Russell |  |  |  |  | 8/8 On Hold per UPB. | Banner Human Resources | No | 2016-08-08
UPB-1016 Modifications to the Tuition Waiver Query | Modifications to the Tuition Waiver Query |  | ADSD | WR - ADSD HR Payroll |  | Lasticly, Andrea M | Low | Medium | 1 | 2014-08-29 | Stone, David |  |  |  |  | 8/8 UPB began testing current version around 9/1. Andrea will follow up on the status. | Tuition Waiver | No | 2016-08-08
UPB-1015 Automate UPB Audit Queries | UPB has several queries they run manually via TOAD with each BW, MN and adjustment payroll. We need to work with UPB to automate the queries. They have placed the queries and their priorities in a folder on the AITS/UPB shares. |  | ADSD | WR - ADSD HR Payroll |  | Hanyzewski, Larry | Low | Medium | 5 | 2014-08-04 | Robinson, Kathi |  |  |  | 10721, 11088, 11492 | 8/8 Final chain is in production. We will have one final meeting on 6/22/2016 to close this out for now, and put the other chains ON HOLD until later. Changes to existing chains still need to be made, but need to talk to Tom Muehling about best way to handle. |  | No | 2016-08-08 | 2015-01-28
UPB-1012 Report for UPB Training | Needed Report for UPB Training Please see Don Smith's note below with requirements requesting an audit report be available for identified UPB staff to determine payroll access of department users for processing adjustments, time reporting via Banner Forms and the web including all time entry proxies, Workflows associated with adjustment processing, Labor redistributions, One Time Payments, Adjustment Notification Adjustments (ANA), Paris, An example of a similar audit is in the attached where UAFR is provided information for a finance profile. Please let me know what additional information is needed for this request. |  | ADSD | WR - ADSD HR Payroll |  | Hanyzewski, Lawrence V. | Low | Medium | 22 | 2014-05-07 | Robinson, Kathi |  |  |  |  | 8/8 Had a meeting with Don earlier this year and he redid the specs. This may have to wait until after the PARIS reporting that Laura wants. |  | No | 2016-08-08
UPB-1011 Analysis of Monthly/Quarterly Unemployment file | Monthly and Quarterly Unemployment file-logic An issue has been identified by Dave Kittell where an employee gross wages were not shown on the report when some of his earnings are "subject to" and some earnings "not subject to" based on the attributes of his eclass, position, and earn codes. The logic for creating the monthly and quarterly unemployment files needs to be reviewed to determine data consistency. Timothy R. Gavin |  | ADSD | WR - ADSD HR Payroll |  | Gavin, Tim | Low | Medium | 3 | 2013-12-17 | Kittell, David |  |  |  |  | 8/8 On Hold per UPB. Not started. Per LH, this needs to be addressed in 2016. | Illinois Department of Employment Security (IDES) Quarterly Unemployment Eligibi | No | 2016-08-08
UPB-1008 Restricting GXADIRD with FGAC | We need to implement a solution restricting GXADIRD with oracle fine grained access, rather than expanding NEWT to handle non-HR records. |  | ADSD | WR - ADSD HR Payroll |  | Hanyzewski, Larry | Low | Medium | 7 | 2013-08-30 | Robinson, Kathi |  |  |  |  | 8/8 Testing in progress. | Banner Human Resources | No | 2016-08-08
UPB-1007 SSA Deductions Bug on Edit Not Retaining Plan Code | When you look at the parking app for a deduction code that has an associated plan, the Add works great. However, if you go in to edit the deduction (for example to add an adjustment for a specific pay period), it loses the Plan code and won't let you save. Only a problem with parking because parking deductions are the only relevant deductions that contain plan codes. |  | ADSD | WR - ADSD HR Payroll |  | Cummings, Stephanie M | Low | Low | 34 | 2013-03-21 | Cummings, Stephanie | Tsai, Eddie |  |  |  | 8/8 On Hold per UPB. No movement right now. Tested and found a few issues. Sent back to Eddie. | Parking Deduction Application | No | 2016-08-08
UPB-1006 Modification to Adjustment Fidelity Process | Modify the adjustment fidelity process to automatically determine the update date prompt. This will eliminate the need for the adjustment fidelity process to use the HRPAY_FIDELITY_FILE_ADJ parameter editor application to pull in the prompt. |  | ADSD | WR - ADSD HR Payroll |  | Hanyzewski, Larry | Low | Low | 42 | 2013-03-28 | Robinson, Kathi |  |  |  |  | 8/8 On Hold per UPB. Not in progress. Will include removal of sudo scripts and move to com sftp module mimicking new SURS download. | Fidelity | No | 2016-08-08
UPB-1005 Modification to Adjustment Online Earnings Process | Modify the adjustment online earnings process to automatically determine the update date prompt. This will eliminate the need for the adjustment online earnings process to use the HRPAY_FIDELITY_FILE_ADJ parameter editor application to pull in the prompt. |  | ADSD | WR - ADSD HR Payroll |  | Hanyzewski, Larry | Low | Low | 40 | 2013-02-28 | Robinson, Kathi |  |  |  |  | 8/8 On Hold per UPB. This is a little different than the other applications where we've eliminated the need for the parm editor. | Online Earning Statement | No | 2016-08-08
UPB-1004 Calc Engine Modifications | We need the involuntary calc engine updated so employees with multiple garnishments are not over deducted when they qualify for minimum pay. The calc engine also needs to be updated to include the new FIMA tax in all calculations that include SFM and SFN. |  | ADSD | WR - ADSD HR Payroll |  | Bales, Deborah | Low | High | 4 | 2012-11-28 | Combs, Mary |  |  |  | 6715 | 8/8 On Hold per UPB Part #1 complete: 5/30 under CC6715. Part #2: Code change is done - testing in progress. Very difficult to get this scenario to occur in test. | Involuntary Deduction | No | 2016-08-08
UPB-1003 SURS Contribution Audit | Need a query for SURS Contribution data We need a query written on the SURS Contributions Audit in order to determine the impact before making a decision on how to proceed with changes to the process. Please let me know if you have questions and/or need more information. |  | ADSD | WR - ADSD HR Payroll |  | Bales, Deborah | Low | Low | 49 | 2012-11-05 | Stone, David |  |  |  |  | 8/8 On Hold per UPB Dave to send Larry a write-up regarding the issues. Not started. | SURS Contributions | No | 2016-08-08
UPB - 1125 Add Org 538003 to ACES feeder process | Animal Sciences requests to add Org 538003 to ACES feeder process |  | ADSD | WR - ADSD HR Payroll |  | Andrea Lasticly | Low | Low |  | 2016-10-06 | Combs, Mary |  |  |  |  | 10/10 Scripts in progress. |  | No | 2016-10-10
FX259-Next sequence number for Fix | Place holder for the next sequence number for a fix request. |  | ADSD | WR - HR Applications |  |  | Low | Low |  | 2016-07-19 | [7 empty] | No | 2016-12-22
FX258-Update Request Access to Benefit New Hire Forms tool in NEWT to prevent creation of logins for non-active employees | Currently, if a UPB member tries to create a benefits-only login to the UI New Hire system for a non-active (active in PEAEMPL; job status does not matter) employee, the NEWT tool allows this. However, this creates a system conflict that won’t allow HRFE to fully hire that person until the benefits-only t_new_hire_user record is expired/purged. This isn’t a correct situation (a non-active employee gets benefits in this way), so this should be prevented, and an error message should be presented to the UPB user trying to do this, stating that the tool is only to be used for already-active employees. | UA;UIC;UIS;UIUC | HRIS | WR - HR Applications |  | Meg Osfar | Low | Low |  | 2016-12-22 | Osfar, Megan | Le, Quoc | 2017-01-10 | Ready for Production |  |  | NEWT | No | 2017-01-10 | 2017-01-17
FX256-Delete test data from DELTA prod | Would it be possible to delete the test people from the production instance of the DELTA_AWD @ APPSPROD All records for these nomination_ids should be deleted from the following tables: Table: T_NOMINATION_EMPEE Nomination_IDS: 224, 225, 226, 227, 228 Table: T_NOMINATION_EMPEE_HIST Nomination_IDS: 224, 225, 226, 227, 228 Table: T_DELTA_NOMINATION Nomination_IDS: 224, 225, 226, 227, 228 Table: T_DELTA_NOMINATION_HIST Nomination_IDS: 224, 225, 226, 227, 228 Table: T_SUPPORT_DOC Nomination_IDS: 224 Table: T_SUPPORT_DOC_HIST Nomination_IDS: 224 | UA | HRIS | WR - HR Applications | UOHR - University Office of HR | Ernesto Zepeda | Low | Low |  | 2016-12-02 | Zepeda, Ernesto |  | 2017-01-03 | Complete | 15722 |  |  | No | 2017-01-17 | 2016-12-08
FX253-Reporting Portal Issue | Find solution to the ‘- Invalid access’ error occurring after security timeouts in UHR Reporting Portal in DEV/TEST. | UA;UIC;UIS;UIUC | HRIS | WR - HR Applications | UOHR - University Office of HR | Burgener, Todd | Low | Low |  | 2016-07-18 | Royce-Malmgren, Katrina | Stone, Jane | 2016-07-19 | Ready for Development |  | Todd indicated this issue is of medium urgency. Jane indicated she will work on this when time allows. |  | No | 2016-07-31
CR1472-Next sequence number for change. | Place holder to document the next CR number to be used. |  | ADSD | WR - HR Applications |  |  | Low | Low |  | 2016-07-26 | Kerber, Tony | [6 empty] | No | 2016-12-22
CR1471-Add Job aid "Decoding the Payroll Schedule" to Training Framework | New job aid written in Storyline. Record of Completion or the related email not needed, but want to be able to track who’s used the tool. Subject content is decoding the payroll schedule. Looking for a production deployment 1/12/2017. | UA;UIC;UIS;UIUC | HRIS | WR - HR Applications | UPB | Laura Barnett | Low | Low |  | 2016-12-20 | Hays, Martha | Le, Quoc | 2017-01-05 | Complete | Chg15862 | Needed by 1/12/2017 |  | No | 2017-01-17 | 2017-01-10
CR1470-PRMS/Hire Touch Integration for CS Dates | II. With this Change: A. The campuses want the CS last updated dates to be populated in HT according to campus that the applicant actually last submitted the application only. B. They want the PRMS CS last updated date and the HT CS last updated dates to be in synch. C. They want the CS last updated dates to be dependable so that they can be used to accurately do merges in PRMS and Duplicate Matching in HT. | UA;UIC;UIS;UIUC | HRIS - ADSD | WR - HR Hiretouch | HRIS | Martha Boller-Saha | Low | Low |  | 2016-12-19 | Hays, Martha |  |  | Specs in Progress |  |  | HireTouch | No | 2016-12-19
CR1469-New Benefits LTD BDMS form generated at Open Enrollment | UPB needs a new LTD confirmation data written to BDM-Xtender for Open Enrollment. We would like the following: 1. A new doc type will have to be created in BDM-Xtender. 2. Document type will need to be assigned appropriate security. 3. HRIS will need subdirectories added to docmgtprod.admin.uillinois.edu for the PDFs and index files, and our code will need write access to them. 4. A polling job will need to be created | UA;UIC;UIS;UIUC | HRIS | WR - HR Applications | UOHR - University Office of HR | Wendy Doebel | Low | Low |  | 2016-12-01 | Zepeda, Ernesto |  |  | Not Started |  |  | NESSIE | No | 2016-12-05
CR1467-Create Single Sign-On for GIS | GIS has the capability to support Single Sign-On (SSO). This would allow the University to control password expiration policies as opposed to the 60 day password expiration imposed by GIS. | UA;UIC;UIS;UIUC | HRIS | WR - HR Applications | HRIS | Tony Kerber | Low | Medium |  | 2016-11-21 | Zepeda, Ernesto |  |  | Not Started |  | There is a meeting scheduled for 12/5 to discuss next steps. | Tracker I9 | No | 2016-11-28
CR1466-Modifying NESSIE Applications to Adopt UHR Theme | Develop a short term solution to modify current NESSIE applications so that they will reflect the new UHR theme and take advantage of comparable UI New Hire application development. | UA;UIC;UIS;UIUC | HRIS | WR - HR Applications | HRIS | Tony Kerber | Low | Low |  | 2016-11-18 | Kerber, Tony |  |  | Specs in Progress |  |  | NESSIE | No | 2016-11-18
CR1465-Batch Process to Move FLSA Determination Letters to BDMS | UIUC would like a batch process to move Determination Letters related to FLSA to BDMS. The "Letter of Explaination" doc type will be used for these letters. UIC has expressed interest in this process as well. | UIUC | HRIS | WR - HR Applications | UIUC Human Resources | Stephanie Haas | Low | Low |  | 2016-11-16 | Zepeda, Ernesto |  | 2017-01-05 | Specs in Progress |  | Rich Gegg will be able to import the whole set of letters. I've met with Rich to gather some of his requirements. These have been asked to the user. |  | No | 2017-01-09
CR1464-Add New UPB Training Course to HRTRAIN Framework for Terminal Benefits | Add a new training course for UPB to the HRTRAIN framework for Terminal Benefits. DEV/TEST files will be provided by 11/10/16 with a goal to put course into PROD on 11/17/16. Updated dates will be provided on 11/28. | UA;UIC;UIS;UIUC | HRIS | WR - HR Applications | UPB | Laura Barnett | Low | Low |  | 2016-11-09 | Hays, Martha | Le, Quoc |  | Specs in Progress |  | Laura will provide a status update on Monday 11/23/16 with new proposed target date. |  | No | 2016-11-23
CR1463-Accomidating New UPB Phone System | UPB is getting a new phone system that will go live on 11/29. On 11/29 there will be a single phone number for payroll and benefits at Urbana and another for Chicago. The Urbana and Chicago numbers will be the current payroll phone number. Springfield will keep Susan Patterson’s number as their payroll/benefits phone number. | UA;UIC;UIS;UIUC | HRIS | WR - HR Applications | UOHR - University Office of HR |  | Low | Low |  | 2016-11-07 | Kerber, Tony | Le, Quoc |  | Development in Progress |  |  |  | No | 2016-11-28
CR1462-Masking of Select Data in NESSIE | The University Security Group has recommended that some data in NESSIE be masked. They have asked that HR review the display of SSN, Drivers License, UIN and Date of Birth. | UA;UIC;UIS;UIUC | HRIS | WR - HR Applications | HRIS | Tony Kerber | Low | Low |  | 2016-11-07 |  |  |  | Not Started |  | To be presented at HRFE/PARIS Steering Team for their feedback. | NESSIE | No | 2016-11-07
CR1461-Analysis for the Support of Pretty Names for Job Titles | Most job titles are in caps and are abbreviated. For example, DATABASE APP PGMR. There have been some inquires into establishing a new field in Banner that could accommodate a more meaningful title. Once populated in Banner this title could be available in the EDW. This work request would look at what it might take to maintain and administer a Pretty Name for a Banner Title. This work request was initiated based on a CCSP dicussion on Pretty Names for Job Titles | UA;UIC;UIS;UIUC | HRIS - ADSD | WR - HR Analysis | HRIS | Dimuthu Tilakaratne | Medium | Low |  | 2016-10-21 | Kerber, Tony |  |  | Not Started |  |  |  | No | 2016-10-25
CR1459-Vendor Delivered TitleIX Training for New Hires | The University Ethics and Compliance Office would like the new interactive EverFi Title IX training added to the UI New Hire forms, instead of using the current Captivate training. |  | HRIS | WR - HR Applications | Ethics | Donna McNeely | Low | Medium |  | 2016-10-14 | Osfar, Megan |  | 2016-12-13 | Specs in Progress |  | Current info is being incorporated into the spec, but a production date for the underlying infrastructure is still needed. | UI New Hire | No | 2016-12-13
CR1456-Create tool to remove UI New Hire benefits records created in error | HRIS would like a utility that can be used to remove the UI New Hire demographic information record that is created either through the submission of the demographics form or EIF in UI New Hire. This could be used to remove records after testing in production with current IDs or could be used if a person submits the EIF/demographics verification form with incorrect information and it is caught before the data bridges (such as in the case of an EIF or Demographics Verification form submitted with an incorrect name, SSN, email address, etc.). |  | HRIS | WR - HR Applications | HRIS | Jane Stone | Low | Low |  | 2016-10-05 | Osfar, Megan |  |  | Not Started |  |  | NEWT | No | 2016-10-05
CR1451-Modify Tuition Waiver Email Text | Change the body of the Child of Employee 50% Waiver to: The attached Tuition Waiver Form has been received and is being forwarded to the Office of Student Financial Aid for processing. | UIUC | HRIS | WR - HR Applications | UIUC Human Resources | Michelle Trame | Low | Low |  | 2016-09-12 | Hays, Martha | Le, Quoc |  | Ready for Development |  | The spec is attached for this change. Their is no hard deadline established for this change. | NESSIE | No | 2016-11-28
CR1449-Review of Appointment Types on EVS Statements | UIC is requesting a review of appointment types that display in the position summary versus additional earnings on the Historical Earnings, Current Earnings, Current Employment, and Historical Employment statements. | UA;UIC;UIS;UIUC | HRIS | WR - HR Applications | UIC Human Resources | Amira Ghadeer | Low | Low |  | 2016-08-11 | Osfar, Megan |  |  | Not Started |  |  | NESSIE | No | 2016-08-11
CR1444-New Batch Job to process ANCRA paper training files for polling job |  | UA;UIC;UIS;UIUC | HRIS | WR - HR Applications | UOHR - University Office of HR | Ken Gilmore, Cassaundra Staudacher | Low | Low |  | 2016-06-21 | Osfar, Megan |  |  | Specs in Progress |  |  |  | No | 2016-06-21
CR1439-Process to purge paper and BDMS Form I9s | We’ve identified records in Tracker to purge but there is a larger purge that needs to happen, a paper purge of eligible hard copy records and BDMS records | UA;UIC;UIS;UIUC | HRIS | WR - HR Applications | HRIS | Cathy Menacher/Laura Czys | Low | Low |  | 2016-05-10 | Zepeda, Ernesto |  | 2016-10-07 | Specs in Progress |  | The priority has been set to Low. | Tracker I9 | No | 2016-10-17
CR1438-Analysis to Eliminate Generic Extra Help ID/PW | Perform the analysis leading to eliminate the need for the generic extra help ID/PW | UA;UIC;UIS;UIUC | HRIS | WR - HR Analysis | HRIS | Tony Kerber | Medium | High |  | 2016-05-04 | Kerber, Tony |  |  | Specs in Progress |  |  |  | No | 2016-05-04
CR1435-Masking routing numbers in Earnings Statement/Direct Deposit | The security issues team has requested that Routing Numbers also be masked in Direct Deposit/Earnings Statement. UPB (Larry) has approved this request and would like it added to NESSIE/UI New Hire as soon as possible after account numbers are masked. | UA;UIC;UIS;UIUC | HRIS | WR - HR Applications | UPB | Larry Hanyzewski | Low | Low |  | 2016-04-22 | Royce-Malmgren, Katrina |  |  | Not Started |  |  | NESSIE | No | 2016-08-18
CR1433-Add Clean Address verification to EIF-Emergency Contacts forms | Clean Address verification is currently running on the PPADIEN Emergency Contacts addresses. AITS has requested we add this to the EIF-Emergency Contact forms in UI New Hire and NESSIE that write to this Banner form (only for U.S. addresses). They have stated this is not a high-priority item, but should be done for consistency. | UA;UIC;UIS;UIUC | HRIS | WR - HR Applications | ADSD - Appl. Dev. Supt. & Data | Robyn Velazquez, Teresa Woodley, and Sta | Medium | Low |  | 2016-04-11 | Kerber, Tony |  |  | Not Started |  |  |  | No | 2016-04-11
CR1431-Modification to the LDAP field in Report Inventory | UHR Information Management (IM) would like to make some changes to the report inventory LDAP field that we added recently in CR 1385 Report Inventory Changes. • allow multiple values to be selected • add “obfsTrainingReporting” as a choice in this field • not a critical change, but in the Edit mode the font for this field is much larger than the rest of the items https://hrnet.uihr.uillinois.edu/newt-cf/reporting/inventory/index.cfm Priority: Medium Target Date: April 21 (if possible) | UA;UIC;UIS;UIUC | HRIS | WR - HR Applications | UOHR - University Office of HR | Susan Gerini | Low | Medium |  | 2016-04-06 | Zepeda, Ernesto | Le, Quoc | 2017-01-05 | Development in Progress |  | The multiple option selection change has been completed along the other two. The database of the application was restructured so the application will be tested thoroughly by Susan's group. |  | No | 2017-01-09
CR1429- Ability to update an applicant status in PRMS from HT | Pilot for updating an applicant status in PRMS from HT. When an applicant status is updated in HT, it will be updated in PRMS on the register. The applicant status and exam status would be sent over. For example, the status in HT “Doesn’t meet MAQ” should turn into “Denied” in PRMS. Kathy thinks that it would be a completely new Coldfusion webservice. The implementation would be done by campus. Chicago would like to have it as High priority. Urbana would also use it in the future. Springfield would also benefit from the use of it. Level of effort: medium with all pieces in sync. This will require the specifications be sent to Imagetrend for their assessment. | UA;UIC;UIS;UIUC | HRIS | WR - HR Hiretouch | UIC Human Resources | Ken Scott | Medium | High | 6 | 2016-03-25 | Zepeda, Ernesto |  | 2016-06-17 | Specs in Progress |  | This was presented by UIC but UIS & UIUC are interested in using it at some point. on hold pending review of similar CRs. | HireTouch | No | 2016-10-21
CR1427-Modify Self Service Apps to Use and Maintain Preferred First Name | Once ITPC-0519 Preferred First Name Implementation is completed, changes can be made to selected NEWT, NESSIE and UI New Hire applications. This will allow an employee to create and maintain their preferred first name. In some cases the preferred first name will be displayed instead of the employee's legal name. | UA;UIC;UIS;UIUC | HRIS - ADSD | WR - HR Applications | HRIS | Tony Kerber | Medium | Low |  | 2016-03-24 |  |  |  | Not Started |  | This will also impact NESSIE, NEWT, UI New Hire and PTR | UI New Hire | No | 2016-04-11
CR1426-Change UI New Hire NetID claiming flow to include AITS-RAVE integration | three campuses different RAVE implementations/databases. UI New Hire will need to call this integration during the NetID claiming process (either on the shared “Set NetID password in MidPoint” screen or on a standalone screen) once it’s available. The date on this is TBD – it is currently not known if this will be happening prior to or after the OIDPW UIC NetID claiming process goes live. | UA;UIC;UIS;UIUC | HRIS | WR - HR Applications | HRIS | Suzanne Zelle and Butch Zunich | Low | Low |  | 2016-03-11 | Osfar, Megan | Kammin, Michael | 2016-12-06 | Specs in Progress |  | Next design meeting on January 9, 2017. | UI New Hire | No | 2016-12-06
CR1424-2017 LTD Open Enrollment | 2017 LTD Open Enrollment: NESSIE app needed for an upcoming OE period along with a new BDMS form for “LTD Open Enrollment.” | UA;UIC;UIS;UIUC | HRIS | WR - HR Applications | UOHR - University Office of HR | Doebel, Wendy | Medium | Low |  | 2016-02-19 | Zepeda, Ernesto | Stone, Jane | 2016-11-14 | Testing in Progress |  | Testing is in progress | NESSIE | No | 2017-01-09
CR1422-Addendum to OPA – ability to add information to a closed PA and other fixes | Addendum to OPA - ability to add information to a closed PA using an additional form and other items. Tentative production data is 7/7 | UA | HRIS | WR - HR Applications | UOHR - University Office of HR | Denise Swenson | Medium | Medium |  | 2016-02-11 | Zepeda, Ernesto | Le, Quoc | 2016-10-10 | Testing in Progress |  | Testing is in progress. |  | No | 2017-01-12
CR1410-New UIS HireTouch Workflow for Faculty and AP Waivers | New Workflow for Faculty and AP Waivers so that they can be asked to fill out an employee application in HT and have a record in HT. | UIS | HRIS | WR - HR Hiretouch | UIS Human Resources | Melanie Trimm | Medium | High |  | 2015-11-19 | Hays, Martha |  |  | Testing in Progress |  | This was completed for Faculty workflow. It needs to be duplicated and for AP and added to production. | HireTouch | No | 2016-03-03
CR1408-Create a New Front & Login Page for UIS HireTouch | Create a New front page and Login landing Page for UIS | UIS | HRIS | WR - HR Hiretouch | UIS Human Resources | Melanie Trimm | Medium | High |  | 2015-11-19 | Hays, Martha |  |  | Development in Progress |  | The login landing page is complete but the Front page is not. | HireTouch | No | 2016-02-01
CR1407-Update/Review Springfield CMS configuration | Update/Review Springfield CMS configuration to improve and re-organize public site pages and information organization. (Springfield) | UIS | HRIS | WR - HR Hiretouch | UIS Human Resources | Melanie Trimm | High | Medium |  | 2015-11-19 | Hays, Martha |  |  | Ready for Production |  | This is completed in UAT and ready to move to Staging and Production. | HireTouch | No | 2016-02-01
CR1406-Create New Security Group for UIS HireTouch | Create new security groups tailored to ERHR staff to access UA CS Jobs residing on UIS enterprise/campus and not UIS SHR jobs unrelated to ERHR searches. | UIS | HRIS | WR - HR Hiretouch | UIS Human Resources | Melanie Trimm | Low | High |  | 2015-11-19 | Hays, Martha |  |  | Not Started |  | This has not been started. Both the UA and UIS would like this change request completed. | HireTouch | No | 2016-02-01
CR1405-Create new CS Job Category for UIS in HireTouch | Create new CS Job Category, and UA/workflow and forms for UIS enterprise so that (ERHR). | UIS | HRIS | WR - HR Hiretouch | UIS Human Resources | Melanie Trimm | High | High |  | 2015-11-19 | Hays, Martha |  |  | Not Started |  | This has not been started but Jami has asked that be made a top priority to be completed. This should be worked together with CR 1377 & CR 1406 to be most effective. | HireTouch | No | 2016-02-01
CR1397-Migrate to New Version of Tracker (Scarlet) | Implement the new version of Tracker I9. The new version is referred to as “Scarlet”. The APIs will be based on JSON instead of REST. This will require changes to the HRFE integration with Tracker I9 and the termination date batch updates. | UA;UIC;UIS;UIUC | HRIS | WR - HR Applications | HRIS | Tony Kerber | High | Low |  | 2015-11-02 | Zepeda, Ernesto |  |  | Not Started |  | The implementation is tentatively scheduled for 4th quarter of 2017 | Tracker I9 | No | 2016-11-16
CR1391-Change Driver's License Edit pop-out window in UI New Hire | Currently, the Driver’s License form in the EIF allows updates of most fields on “Edit”. However, we’ve discovered the Banner table PAYROLL.PPRDLIC has a grouped primary key for driver’s licenses that include DL number, PIDM, and Issue Date, certain fields aren’t being updated on the edit (but also aren’t transmitting errors to the users saying that their fields weren’t updated) (I found this in the REPTPROD, but we need to do a short analysis of this within the Banner PPAGENL form to ensure there aren’t addition form-based constraints on this, as Nation/State of issue has possibly shown this behavior as well). We would like for the Edit “pop-out” window to list all uneditable fields as such (by being greyed-out). Additionally, a line of text should be added explaining that only certain fields are editable and that, if the user has made an error that includes a non-editable field, they should delete and re-add a license. | UA;UIC;UIS;UIUC | HRIS | WR - HR Applications | UIUC Human Resources | Nicole Peck and Cathy Menacher | Low | Low |  | 2015-09-28 | Osfar, Megan |  |  | Not Started |  |  | UI New Hire | No | 2016-01-25
CR1377-UIS HireTouch CS Update | Establish a tailored version of UIC CS workflow on the UIS campus to utilize the new exam request functionality on the UIS campus for the UIS SHR and the UA ERHR HT users, and applicant job postings. | UIS | HRIS | WR - HR Hiretouch | UIS Human Resources | Melanie Trimm | High | High |  | 2015-07-21 | Hays, Martha | Hays, Martha | 2015-07-21 | Not Started |  | This new exam request functionality will solve many of the struggles that UIS has been trying to resolve, I think this request along with CR 1405 and CR 1406 should be made a priority after the 1st of the year. | HireTouch | No | 2016-03-24
CR1376-UIS/UA HireTouch CS Update | Create UA C.S. Job Category, Workflow for Custom Titles using new C.S. exam request functionality on the UIS enterprise. UA & UIS now has an agreement for UA/ERHR to do the admin work for CS on the Springfield campus for UA jobs. The creation of their own Job category, workflow and UA C.S. Employee requisition will enable the C.S. jobs and access for UIS and UA on the UIS enterprise to remain separate. The custom classes that will be created with this Change request will be as follows: Business Administrative Associate – 5010 Human Resources Associate – 5020 IT Technical Associate – 5031 IT Technical Support Associate – 5032 Accounting Associate – 5000 | UA;UIS | HRIS | WR - HR Hiretouch | UOHR - University Office of HR | Angela Foster/Melissa McMullen | High | Medium |  | 2015-07-21 | Hays, Martha | Hays, Martha |  | Not Started |  |  | HireTouch | No | 2016-03-24
CR1374-SURS Contribution Max Application | Faculty and other employees ask UIC-HR why contributions have stopped, and UIC-HR assumes it’s because they’ve reached their SURS Max. They are creating a report that shows who has hit their max so that they can more easily answer this questions, but would like this included in NESSIE, too, as an employee application. | UA;UIC;UIS;UIUC | HRIS | WR - HR Applications | UIC Human Resources | Amira Ghadeer | Low | Low |  | 2015-07-03 | Osfar, Megan |  | 2015-07-09 | On Hold |  | This is on hold until the reports are finished. The queries used for the reports are needed for the NESSIE application, so this should not begin until those are finalized. |  | No | 2016-11-14
CR1371-AD&D Create Error: Effective Date Prior to Last Paid Date | UI New Hire and NESSIE: AD&D currently calculates an effective date based on the current date and the employee’s hire date. Whichever is greater is considered the effective date for any contribution they add. The employee can’t select the effective date on the AD&D form. | UA;UIC;UIS;UIUC | HRIS | WR - ADSD HR Payroll | UPB | Becker, Zac | Low | Low | 59 | 2015-06-25 | Royce-Malmgren, Katrina |  | 2016-07-19 | Specs in Progress |  |  | NESSIE | No | 2016-11-17
CR1342-Employment Verification Enhancement of last pay change date | UIUC is requesting that the last pay change date be included on the EVS statements generated from NESSIE, NEWT, or the External UHR app. This should be on a per-job basis (not just pulled from the general employee info), as many employees have more than one job and raise dates will vary by job. This also should specifically check for a rate raise (versus just a situation where an hourly employee has started working more hours). We don’t currently pull this information in, per a conversation with the developer, and will need a change to a stored procedure (or a new stored procedure written) to get this information so that it displays the above situations correctly. This is something that was mentioned as being desirable by the other campuses during EVS update meetings. All campuses should be consulted as to look/feel/layout, but the inclusion of this information can already be considered to have all-campus support. | UA;UIC;UIS;UIUC | HRIS | WR - HR Applications | Human Resources | Michelle Althaus | High | Low |  | 2015-02-20 | Osfar, Megan |  | 2016-12-09 | Not Started |  |  |  | No | 2016-12-09
CR1337-Change Options for Simultaneous SESSIONS_PER_USER limit | Look at programming options to eliminate the Simultaneous SESSIONS_PER_USER limit error in the HireTouch to PRMS candidate extract process. | UA;UIC;UIS;UIUC | HRIS | WR - HR Hiretouch | HRIS | Tony Kerber | Low | Low |  | 2015-01-15 | Kerber, Tony | Stone, Jane | 2016-01-25 | Not Started |  | This is an internal HRIS project. |  | No | 2016-03-03
CR1297-Create New Faculty Search Merge templates (Springfield) | Create New Faculty Search and AP Title/Faculty Search Merge templates for hybrid workflow to notify provost and search coordinator. (Springfield) | UIS | HRIS | WR - HR Hiretouch | UIS Human Resources | Melanie Trimm | Low | Low |  | 2014-09-10 | Hays, Martha |  |  | Not Started |  |  | HireTouch | No | 2016-03-24
CR1296-Create New UIS workflow Faculty Search and AP Title and Faculty Search (Springfield) | Create New UIS workflows, Faculty Search and AP Title/Faculty Search (Springfield) | UIS | HRIS | WR - HR Hiretouch | UIS Human Resources | Melanie Trimm | Low | Low |  | 2014-09-10 | Hays, Martha |  |  | Not Started |  |  | HireTouch | No | 2016-03-24
CR1295-Update Security Groups (Springfield) | Update/Review Security Groups (Springfield) | UIS | HRIS | WR - HR Hiretouch | UIS Human Resources | Melanie Trimm | Low | Low |  | 2014-09-10 | Hays, Martha |  |  | Not Started |  |  | HireTouch | No | 2016-03-24
CR1294-Update Springfield CMS configuration | Update/Review Springfield CMS configuration to improve and re-organize public site pages and information organization. (Springfield) | UIS | HRIS | WR - HR Hiretouch | UIS Human Resources | Melanie Trimm | Low | Low |  | 2014-09-10 | Hays, Martha | Hays, Martha |  | Not Started |  |  | HireTouch | No | 2016-03-24
CR1293-Update C.S. workflow (Springfield) | Update/Review C.S. workflow (Springfield) | UIS | HRIS | WR - HR Hiretouch | UIS Human Resources | Melanie Trimm | Low | Low |  | 2014-09-10 | Hays, Martha |  |  | Not Started |  |  | HireTouch | No | 2016-03-24
CR1292-Update C.S. Public Site Page (Urbana) | Update C.S. Public Site Page (Urbana) per specifications on attachment. | UIUC | HRIS | WR - HR Hiretouch | UIUC Human Resources | Becky Janowski | Low | Low |  | 2014-09-10 | Hays, Martha |  |  | Not Started |  |  | HireTouch | No | 2016-03-24
CR1291-Update C.S. Application PDF (Urbana) | Update C.S Application Forms on the Urbana Enterprise, Change the PDF to appear like attachment, which more like the view in NEWT. | UIUC | HRIS | WR - HR Hiretouch | UIUC Human Resources | Becky Janowski | Low | Low |  | 2014-09-10 | Hays, Martha |  |  | Not Started |  |  | HireTouch | No | 2016-03-24
CR1223-Modify PRMS HireTouch Web Service for UIC Non-Required Fields | Modify web service for HireTouch/PRMS feed so that specific UIC non-required fields will populate with a default value. | UIC | HRIS | WR - HR Applications | UIC Human Resources | Ken Scott | Medium | High |  | 2013-12-04 | Zepeda, Ernesto | Stone, Jane | 2016-12-20 | Waiting for Approval |  | Chicago has signed off on the specifications. Indicated it is a high priority item. |  | No | 2017-01-09
CR1206-Add Faculty/Administrative Search to UIS HireTouch | Springfield would like a new job template and workflow added for Faculty/Administrative Search. The first job form to complete will be the position requisition form and once it is approved the faculty search plan would be attached and would follow the same workflow as faculty search for the remaining steps. | UIS | HRIS | WR - HR Hiretouch | UIS Human Resources | Melanie Trimm | Low | Low |  | 2013-10-14 | Hays, Martha | Hays, Martha | 2014-01-10 | Not Started |  |  | HireTouch | No | 2016-03-24
CR1204-Phase III OPA changes: Submit to Manager and Add Manager Competencies buttons | Phase III of OPA enhancements | UA | HRIS | WR - HR Applications | UOHR - University Office of HR | Angela Foster | Medium | Medium |  | 2013-10-03 | Zepeda, Ernesto | Le, Quoc | 2016-10-10 | On Hold |  | OPA enhancements will come after a review of current operation Denise. These requests will be looked at after CR1422 is in production (scheduled for end of October). |  | No | 2016-10-10
CR1173-eTest PRMS Integrations | The HR offices would like to have integrations built between the PRMS application and the State Universities Civil Service Systems (SUCSS) eTest system. Data to be exchanged would include exam schedules, results, and register data. Meetings are being scheduled to better define the requirements. | UIC;UIS;UIUC | HRIS | WR - HR Applications | Human Resources | Tony Kerber | High | Medium |  | 2013-07-22 | Zepeda, Ernesto | Nash, Katherine | 2016-10-10 | On Hold |  | On Hold. |  | No | 2016-10-10
CR1118-UA Job Description Maintenance Application | Create an application that can be used to maintain job descriptions for UA employees. Integration with the new UA performance application would be desired. | UA | HRIS | WR - HR Applications | UOHR - University Office of HR | Angela Foster | Low | Low |  | 2013-02-07 | Zepeda, Ernesto | Le, Quoc | 2016-10-10 | On Hold |  | ER/HR would like this tied into CR1204 Phase III OPA Changes. Same status. |  | No | 2016-10-10
CR1097-Modify Employee Requisition Feed for Position Data | The HR offices would like for position information to be added/updated in PRMS when an employee requisition is fed from HireTouch. This will require changes to the PRMS jar file that is used along with the web service and HireTouch. | UA;UIC;UIS;UIUC | HRIS | WR - HR Applications | Human Resources | Ken Scott | High | High | 5 | 2012-12-13 | Zepeda, Ernesto | Stone, Jane | 2016-10-10 | On Hold |  | This will be part of a CR review with the Chicago SMEs | HireTouch | No | 2016-10-10